## Initial
IssueID | $Customer | Component | Summary | Type | SubType | Priority | Status | $AwaitingSolution# | ReportedDate | $PDD(L2) | $PDD(DEV) | $PlannedDeliveryDate | $CommittedDeliveryDate | CodedByName | $Solvedby | $Re-OpenReason | $Re-OpenReasonDetails | ClosedDate
100975 | General Equipment and Supplies Inc | Finance | Help Request->51367-->Select Invoices for payment options | Roadmap | Enhancement | Low | Solution PublishedX | <Not Specified> | 29, Mar 2018 | <Not Specified> | 12, Feb 2024 | 16, Feb 2024 | <Not Specified> | vbhaganagare | Product Solution | <Not Specified> | <Not Specified> | <Not Specified>
279278 | Burns Industrial Equipment (BIE) | Finance | BRD - Check Printing | Development | Functionality | High | Solution PublishedX | <Not Specified> | 07, Dec 2023 | 14, Dec 2023 | 12, Jan 2024 | 19, Jan 2024 | 20, Jan 2024 | schattaraj | <Not Specified> | <Not Specified> | <Not Specified> | <Not Specified>
285264 | Farm Supplies Ltd (FSL) | Parts | Help Request->158602-->Finance-PGI-300 | Maintenance | Not a Bug | High | Solution PublishedX | <Not Specified> | 01, Feb 2024 | 09, Feb 2024 | <Not Specified> | <Not Specified> | <Not Specified> | kavishs | <Not Specified> | <Not Specified> | <Not Specified> | 15, Feb 2024
275798 | Volvo Construction Equipment (VCE) | Parts | Help Request->152363-->Request for cosmetic changes to the four invoices at VCES | Maintenance | Change Request | Medium | Solution PublishedX | <Not Specified> | 06, Nov 2023 | 10, Nov 2023 | <Not Specified> | <Not Specified> | <Not Specified> | sjadhav | Roadmap | <Not Specified> | <Not Specified> | 13, Feb 2024
280210 | MH Logistics Corp. (MHL) | Service | Help Request->155955-->Expiring Units on RAMP Contracts | Maintenance | Bug | Medium | Solution PublishedX | MFD Updated | 15, Dec 2023 | 01, Feb 2024 | 13, Feb 2024 | 16, Feb 2024 | 21, Feb 2024 | tkarandikar | Product Solution | <Not Specified> | <Not Specified> | 14, Feb 2024
285919 | Associated Supply Company (ASCO) | Finance | Column Label issues | Maintenance | Bug | <Not Specified> | ResolvedX | <Not Specified> | 07, Feb 2024 | <Not Specified> | 14, Feb 2024 | <Not Specified> | <Not Specified> | vbhaganagare | Product Solution | <Not Specified> | <Not Specified> | <Not Specified>
255768 | SMS | Finance | Help Request->99388-->Assets Missed on the Depreciation Job | Maintenance | Bug | High | Solution PublishedX | <Not Specified> | 16, May 2023 | 24, Jan 2024 | 30, Jan 2024 | 16, Feb 2024 | <Not Specified> | jrathod | Product Solution | <Not Specified> | <Not Specified> | 14, Feb 2024
265005 | Carter Machinery Company Inc. (CMC) | Parts | DMS-2421 GPO Enhancements (CRP2) | Development | New Dev No SoW | <Not Specified> | OpenX | <Not Specified> | 02, Aug 2023 | 30, Oct 2023 | 22, Dec 2023 | 10, Feb 2023 | <Not Specified> | tkale | <Not Specified> | <Not Specified> | <Not Specified> | <Not Specified>
272523 | Carter Machinery Company Inc. (CMC) | Service | SMCS Codes Development 2.0 | Development | New Dev No SoW | <Not Specified> | OpenX | <Not Specified> | 08, Oct 2023 | <Not Specified> | 22, Jan 2024 | 31, Jan 2024 | 09, Feb 2024 | msawant | Product Solution | <Not Specified> | <Not Specified> | <Not Specified>
284505 | Burns Industrial Equipment (BIE) | Finance | When printing invoice with Equipment Source without reprint label, logo not appearing | Maintenance | Change Request | Low | Solution PublishedX | <Not Specified> | 25, Jan 2024 | <Not Specified> | 13, Feb 2024 | 16, Feb 2024 | <Not Specified> | mjoshi | Product Solution | <Not Specified> | <Not Specified> | 15, Feb 2024
286118 | Titan Machinery Inc (TMI) | Parts | Help Request->159235-->Unable to edit IT0000989 | Maintenance | Bug | High | Solution PublishedX | <Not Specified> | 08, Feb 2024 | 15, Feb 2024 | <Not Specified> | <Not Specified> | <Not Specified> | rgaidhani | Product Solution | <Not Specified> | <Not Specified> | 15, Feb 2024